## Execution Summary
Main-DB End-to-End Flow Test — Execution Summary
Date | 15-Aug-2026
Application | Avarsh Garment ERP (avarsh-erp-ui + erp-purchase)
Environment | dev profile — main dev DB (Neon PostgreSQL), Flyway v28 (V27 production PO + V28 material issue applied this run)
UI | React 19 + Vite 7 + Ant Design 6 on http://localhost:3000
API | Spring Boot 3.4 / Java 21 on http://localhost:8088
Method | Browser-driven testing (Chromium) with API and direct SQL verification after each step
Scope | Costing → BOM → Order → Purchase Order → GRN → QC → Stock → Cutting PO → Fabric Issue → Work Order → Accessories Issue
Metric | Value
Scenarios executed (main DB) | 29
Passed | 29
Passed on first attempt | 26
Passed after same-day defect fix | 3
Failed at end of run | 0
Defects found (all fixed this session) | 3
Gaps open (product decision / refinement) | 2
Observations logged | 4
Automated regression (Playwright production-po, fresh H2) | 6 / 6 passed in 1.2 min
Verdict | CHAIN COMPLETE — all scenarios green on the main database. Open gap G1 (UOM conversion) needs a product decision before real-data go-live of fabric issues.

## Scenarios
Module | ID | Scenario | Expected Result | Actual Result | Status
Login | AUTH-01 | Sign in to dev environment as superadmin | Dashboard loads with live stats | Dashboard shows 2 orders, 2 BOMs; recent-orders table populated | Pass
Costing | CST-01 | Cost sheet list renders approved sheets with pricing | Approved sheets listed with FOB prices and status tags | CST/26-27/1012–1014 listed, all Approved, FOB $6.24–$9.01 | Pass
Orders | ORD-01 | Confirmed orders visible with values | Both seeded orders listed as Confirmed | SG/26-27/1001 ($48,650) and SG/26-27/1002 ($36,400) Confirmed | Pass
Orders | ORD-02 | Order auto-moves to IN_PRODUCTION on first Cutting PO approval | Status flips CONFIRMED → IN_PRODUCTION once | ord_orders shows SG/26-27/1001 = IN_PRODUCTION after CPO approval | Pass
BOM | BOM-01 | BOM list renders created BOMs | 2 BOMs with status Created | Both BOMs listed (4 + 3 lines) | Pass
Purchase Orders | PO-01 | PO list renders completed procurement POs | 3 POs Completed with suppliers and values | PO/26-27/1001–1003 (Arvind, Coats, YKK) all Completed | Pass
GRN | GRN-01 | GRNs close automatically on QC approval | QC_Pending → Closed for all 3 GRNs | All 3 GRNs Closed after QC approvals | Pass
QC — Fabric | QCF-01 | GRN dropdown offers only fabric GRNs | Only fabric GRN selectable | Only GRN/26-27/1001 offered; accessories GRNs routed to Accessories QC | Pass
QC — Fabric | QCF-02 | Per-roll pass/fail against ±5% width/GSM tolerance | Within tolerance → PASS | First attempt force-FAILED because item has no standard width (Defect D1); PASS after fix | Pass (after fix D1)
QC — Fabric | QCF-03 | All 9 QC parameters required on submit (numeric + grade ratings) | Submit blocked until every parameter has an actual | All actuals entered; PASSED result panel shown | Pass
QC — Fabric | QCF-04 | Submit → approve → stock materialisation | QC Approved; GRN Closed; fabric stock rows created | QC/26-27/1001 Approved; rolls 1,903.125 + 140 created In_Stock | Pass
QC — Accessories | QCA-01 | Thread line inspection: qty verdict Matched + criteria OK | QC approved; accessories stock created | QC/26-27/1002 Approved; thread + label stock rows created | Pass
QC — Accessories | QCA-02 | Zipper line inspection (GRN/26-27/1003) | QC approved; zipper stock created | Approved; ZIP-MET-001 3,500 PCS In_Stock | Pass
Stock | STK-01 | Fabric stock feeds production stock-by-BOM panel | Current/free stock reflects QC-passed rolls | 1,903.125 Single Jersey + 140 Rib visible with order/free split | Pass
Stock | STK-02 | Accessories stock feeds trim panel | Thread/label stock visible | Initially 0 — stock rows had null item_id (Defect D2); visible after fix + backfill | Pass (after fix D2)
Masters — Factory | FAC-01 | Active factory available to production PO forms | At least one active factory selectable | Dev DB had none; UNIT-1 created via API (Observation O2: no seed / standalone screen) | Pass
Cutting PO | CPO-01 | Eligible-order lookup (Confirmed + Created BOM) | Qualifying orders offered with context | Both orders offered with style, buyer, BOM | Pass
Cutting PO | CPO-02 | PP-sample gate with in-form "Mark PP Approved" button | Pending banner blocks submit; button flips gate live | Gate flipped live; pp_sample_status = COMPLETED | Pass
Cutting PO | CPO-03 | Create, bulk-rate and submit Cutting PO | PO approved (auto — no approval flow configured); warnings surfaced | CPO/26-27/1001 Approved; 7,350 pcs @ ₹12.50; over-qty warning modal confirmed | Pass
Cutting PO | CPO-04 | Fabric soft allocation written on approval | ACTIVE allocations for fabric items | Allocations written for both fabrics (Rib inflated — Gap G2) | Pass (gap G2 noted)
Fabric Issue | FIS-01 | Approved CPO offered with BOM-derived fabric lines | CPO and its fabric lines selectable | CPO + Single Jersey / Rib lines offered (both show CAD-based figure — Gap G2) | Pass
Fabric Issue | FIS-02 | Issuable rolls listed from real GRN stock | In_Stock rolls with remaining qty listed | Initially empty — free stock misread as earmarked (Defect D3); rolls listed after fix | Pass (after fix D3)
Fabric Issue | FIS-03 | UOM-mismatch guard | Issue blocked with clear error when stock UOM ≠ BOM UOM | Blocked MTR-vs-KG correctly — exposed missing UOM conversion (Gap G1); test data aligned to proceed | Pass (guard OK; G1 open)
Fabric Issue | FIS-04 | Roll split for partial issue | Sub-roll -A selected for issue; remnant stays in stock | ARV-SJ-NB-001-A (100) auto-selected; remnant 1,803.1 stays | Pass
Fabric Issue | FIS-05 | Save clears stock and relieves allocation | MIS document created; available_qty decremented; allocation relieved | MIS/26-27/1001 COMPLETED; roll 1,903.125 → 1,803.125; allocation 10,657.5 → 10,557.5 | Pass
Work Order | WO-01 | IN_PRODUCTION order remains eligible for Work Orders | Order still offered after status flip | SG/26-27/1001 offered | Pass
Work Order | WO-02 | Create, rate and submit Work Order against approved CPO | WO approved; trim allocations written | WO/26-27/1001 APPROVED @ ₹30/pc; variance warning confirmed; thread + label allocations ACTIVE | Pass
Accessories Issue | AIS-01 | WO lookup with live BOM quantities and available stock | BOM items show real bomQty / available | Thread 210 MTR + labels 7,000 PCS shown with shortage highlighting | Pass
Accessories Issue | AIS-02 | Issue trims FIFO and relieve allocations | MIS document; FIFO stock decrement; allocation relief | MIS/26-27/1002 COMPLETED; thread 210 → 110, labels 7,000 → 2,000; allocations relieved exactly | Pass

## Defects & Gaps
ID | Type | Severity | Module | Summary | Root Cause | Resolution | Status
D1 | Defect | Critical | QC — Fabric | Rolls can never pass QC when the item lacks a standard width/GSM | isWithinTolerance returned false for a null standard; rule duplicated inline in FabricQCInspection.jsx | Missing standard now treated as "not applicable"; panel reuses the shared helper (qcValidation.js) | Fixed & verified
D2 | Defect | Critical | Inventory / GRN | Accessories stock rows created with null item_id — invisible to production lookups and material issue | Accessories GRN lines arrive without item_id; StockPopulationService copied it as-is | Fallback to the PO line's item on materialisation; existing stock rows + GRN lines backfilled via SQL | Fixed & verified
D3 | Defect | High | Material Issue | Free fabric stock hidden from the issuable-rolls picker | Stock orderRef falls back to the PO number when the PO has no sales-order link; picker treated any mismatch as an earmark to another order | Earmark now only applies when orderRef matches a real, different sales order (MaterialIssueLookupService) | Fixed & verified
G1 | Gap | High | Material Issue / BOM | No MTR↔KG UOM conversion — BOM consumes meters, GRN stocks kilograms; guard blocks issue on real data | No secondary→primary UOM factor exists anywhere (same decision as costing CR C-11) | Product decision needed: GSM+width-derived conversion factor, or enforce PO/GRN UOM = BOM UOM. Dev data aligned manually for this run only | Open — needs decision
G2 | Gap | Medium | Cutting PO / Stock | CPO CAD consumption/pc applied to ALL fabric BOM rows | stock-by-bom applies the single cadPerPc override to every fabric row | Rib requirement/allocation inflated (10,657.5 vs ~588 MTR); scope the CAD override to the body-fabric row | Open
O1 | Observation | Low | UI-wide | AntD deprecation warnings (Tooltip overlayInnerStyle, Space direction, Modal destroyOnClose) + duplicate select keys on costing list | Pre-existing | Cleanup pass recommended | Open
O2 | Observation | Info | Masters | No factory in dev seed; Factory master only inside HR dashboard tabs | Seed scripts omit factories | UNIT-1 created via API; add a factory to seed-dev.mjs | Open
O3 | Observation | Low | QC — Fabric | 3 pre-existing eslint set-state-in-effect errors in FabricQCInspection.jsx (lines 84/112/122) | Legacy effect patterns | Refactor when the file is next edited | Open
O4 | Observation | Info | Environment | Dev login is superadmin/admin98 (older notes said admin123 — that is the e2e/H2 seed password) | — | Documentation corrected | Closed

## Evidence
Category | Reference | Detail
Document | QC/26-27/1001 | Fabric QC — Approved; closed GRN/26-27/1001; fabric stock materialised
Document | QC/26-27/1002 + zipper QC | Accessories QC ×2 — Approved; closed GRN/26-27/1002 & 1003; trim stock materialised
Document | CPO/26-27/1001 | Cutting PO — Approved; 7,350 pcs @ ₹12.50; order moved to IN_PRODUCTION; fabric allocated
Document | MIS/26-27/1001 | Fabric Issue — COMPLETED; 100 MTR issued from split roll ARV-SJ-NB-001-A
Document | WO/26-27/1001 | Work Order — APPROVED @ ₹30/pc; trim allocations written
Document | MIS/26-27/1002 | Accessories Issue — COMPLETED; 100 thread + 5,000 labels (FIFO)
Stock movement | KNI-SIN-001 / ARV-SJ-NB-001 | 1,903.125 → 1,803.125 (−100 fabric issue); remnant remains In_Stock
Stock movement | SEW-SPU-001 | 210 → 110 MTR (−100 accessories issue)
Stock movement | LAB-WOV-001 | 7,000 → 2,000 PCS (−5,000 accessories issue)
Stock movement | ZIP-MET-001 | 3,500 PCS untouched (control item)
Order status | SG/26-27/1001 | IN_PRODUCTION; pp_sample_status = COMPLETED
Allocations | prd_stock_allocations | 4 ACTIVE rows; relieved by exact issued qtys: Single Jersey 10,657.5 → 10,557.5; thread 1,102,500 → 1,102,400; labels 7,350 → 2,350
Migration | Flyway | V27__production_po.sql + V28__material_issue.sql applied cleanly to Neon; schema at v28

## Automated Regression
Spec | Test | Environment | Duration | Result
setup | authenticate | Fresh H2 (e2e profile) | 4.1s | Pass
01-cutting-po | create, guard rates, submit and approve a Cutting PO | Fresh H2 (e2e profile) | 17.7s | Pass
02-work-order | create a Work Order against the approved Cutting PO and approve it | Fresh H2 (e2e profile) | 16.6s | Pass
03-finishing-po | generate vendor-split Finishing POs and verify coverage | Fresh H2 (e2e profile) | 13.2s | Pass
04-material-issue | issue a partial fabric roll (split) against the approved Cutting PO | Fresh H2 (e2e profile) | 7.4s | Pass
04-material-issue | issue accessories against the approved Work Order | Fresh H2 (e2e profile) | 6.7s | Pass
Total | 6 / 6 passed |  | 1.2 min